## Sheet1
Priority | Who | What | Why | Sprint 1 | Sprint 2 | Sprint 3
0 | As the user | check current weather for given location | So that I can be informed of the current weather in a given location | y
0 | As the user | check warnings (severe weather, air quality, etc) | So that I can be informed of current weather hazards | y
0 | As the user | check weather info based on given time period (hourly, daily, weekly, etc.) | So that I can be more precisely informed of the weather | partial (daily only) | partial (hourly only)
0 | As the user | save locations for future weather checking | So that I can be informed of weather in specific areas | y
0 | As the user | check a weather map based on given location | So that I can be informed over a broader range of locations | n | y | y
0 | as the user | search weather locations nearest me | So that I can get information for weather locations near me easier |  | y
1 | As the user | check previous weather for given location | So I can be informed of previous weather trends | n |  | y
1 | As the user | have the option to maximize the application window | So I can see the information in a bigger window | n | m | y
1 | as the user | change current location manually | So that i can get information pertaining to my location if IP based is not working |  |  | y
Next Steps:
| Wireframe | Finished
| Use cases and diagram | Finished
| Start system design | Finished
| sprint backlog | Finished
Key
| y | yes
| n | no
| m | moved